## Slide 1
MERIDIAN M-27
Fictional, unclassified portfolio demonstration. Status: 2026-09-18
Program Management Review
Current acceptance: 2027-09-21
P80 completion: 2027-10-14
152 leaf activities and milestones
224 dependency links
Notes: All program facts are synthetic. Source: outputs/summary.json and report_data.json. Method: https://www.gao.gov/products/gao-16-89g. No resource leveling.

## Slide 2
Acceptance forecast
Fictional, unclassified portfolio demonstration. Status: 2026-09-18
The current forecast is 18 workdays after the approved baseline.
Chart: 
| Engineering | Software | Logistics | Testing | Delivery
Maximum task finish slip (workdays) | 0 | 24 | 32 | 18 | 18
Baseline: 2027-08-26 Current: 2027-09-21
Notes: All program facts are synthetic. Source: outputs/summary.json and report_data.json. Method: https://www.gao.gov/products/gao-16-89g. No resource leveling.

## Slide 3
Schedule-health findings
Fictional, unclassified portfolio demonstration. Status: 2026-09-18
6 of 14 indicators require review
3. Lags: 12.8%
4. Finish-to-start relationships: 74.4%
6. High float: 5.2%
7. Negative float: 87.9%
11. Missed baseline tasks: 16.9%
13. Critical path length index: 0.931
Mixed SS and FF relationships require justification.
Screening thresholds are diagnostic, not DCMA certification.
Notes: All program facts are synthetic. Source: outputs/summary.json and report_data.json. Method: https://www.gao.gov/products/gao-16-89g. No resource leveling.

## Slide 4
Resource capacity
Fictional, unclassified portfolio demonstration. Status: 2026-09-18
Chart: 
| Design engineering | Software | Logistics | Test | Delivery | Quality review
Peak demand FTE | 0 | 3 | 1 | 4 | 4 | 1
Capacity FTE | 1.5 | 1.5 | 2 | 1.5 | 2 | 1
162 overloaded resource-days. The current forecast remains unlevelled.
Notes: All program facts are synthetic. Source: outputs/summary.json and report_data.json. Method: https://www.gao.gov/products/gao-16-89g. No resource leveling.

## Slide 5
Completion uncertainty
Fictional, unclassified portfolio demonstration. Status: 2026-09-18
P50 2027-10-08
P80 2027-10-14
5,000 seeded trials
0.0% finish by the baseline date
Triangular remaining-duration estimates
Discrete risk occurrence and conditional delay
Actual progress held fixed in every trial
P80 reflects the modeled assumptions. It excludes resource leveling,
holidays and general correlation between duration estimates.
Notes: All program facts are synthetic. Source: outputs/summary.json and report_data.json. Method: https://www.gao.gov/products/gao-16-89g. No resource leveling.

## Slide 6
Change control and decisions
Fictional, unclassified portfolio demonstration. Status: 2026-09-18
CR-001 Approved and applied to current forecast
CR-002 Pending; no forecast change applied
CR-003 Rejected; acceptance baseline unchanged
Decisions requested
Resolve CR-002 before authorizing added scope.
Confirm reviewers and test-team coverage.
Develop a resource-leveled recovery scenario.
Retain the original baseline until a formal rebaseline decision.
Notes: All program facts are synthetic. Source: outputs/summary.json and report_data.json. Method: https://www.gao.gov/products/gao-16-89g. No resource leveling.

## Slide 7
Model scope and assurance
Fictional, unclassified portfolio demonstration. Status: 2026-09-18
Verified in the portable analysis
FS, SS, FF and SF dependency calculations
Baseline variance and separate deadline/network float
Repeatable risk simulation and input diagnostics
Desktop acceptance checks remain
Open Microsoft Project XML and compare dates after recalculation.
Open the native Tableau workbook and verify its CSV connections.
Review Office files in the intended desktop applications.
Notes: All program facts are synthetic. Source: outputs/summary.json and report_data.json. Method: https://www.gao.gov/products/gao-16-89g. No resource leveling.