## Overview
MERIDIAN M-27 ¦ Schedule review
Fictional, unclassified portfolio demonstration
Status date | 2026-09-18 | Reading the report
Original baseline | 2027-08-26
Current acceptance | 2027-09-21 | Dates use a Monday-Friday calendar with no holidays.
P50 completion | 2027-10-08
P80 completion | 2027-10-14 | Risk probabilities and impact inputs are editable on Risks.
Leaf tasks / milestones | 152
Completed items | 78 | Excel exposure and milestone flags recalculate.
Critical remaining | 66
Near-critical remaining | 0 | CPM, resource loading and Monte Carlo require a Python rebuild.
Negative float remaining | 65
At-risk / missed milestones | 16 | Expected task-level risk days are not additive program delay.
Expected task risk days | 39.5667
Overloaded resource-days | 162 | The forecast has not been resource-leveled.
Health indicators for review | 6
Simulation trials | 5000 | See docs/USER_GUIDE.md for refresh and baseline control.
Simulation seed | 27

## Milestones
Milestone reporting
Fictional, unclassified. Status 18 Sep 2026. Derived forecast/SRA fields are Python snapshots.
ID | Milestone | Baseline finish | Current finish | Complete % | Slip workdays | P80 finish | P(on baseline) | Status
T001 | Program authorization | 2026-04-06 | 2026-04-06 | 100 | 0 | 2026-04-06 | 100% | Complete
T006 | Airframe definition: Approval gate | 2026-05-29 | 2026-05-29 | 100 | 0 | 2026-05-29 | 100% | Complete
T011 | Power and thermal: Approval gate | 2026-05-21 | 2026-05-21 | 100 | 0 | 2026-05-21 | 100% | Complete
T016 | Avionics architecture: Approval gate | 2026-07-20 | 2026-07-20 | 100 | 0 | 2026-07-20 | 100% | Complete
T021 | Structural substantiation: Approval gate | 2026-07-15 | 2026-07-15 | 100 | 0 | 2026-07-15 | 100% | Complete
T026 | Prototype integration: Approval gate | 2026-09-03 | 2026-09-03 | 100 | 0 | 2026-09-03 | 100% | Complete
T031 | Design acceptance: Approval gate | 2026-09-03 | 2026-09-03 | 100 | 0 | 2026-09-03 | 100% | Complete
T036 | Platform services: Release gate | 2026-07-15 | 2026-07-15 | 100 | 0 | 2026-07-15 | 100% | Complete
T041 | Telemetry collection: Release gate | 2026-07-10 | 2026-07-10 | 100 | 0 | 2026-07-10 | 100% | Complete
T046 | Health monitoring: Release gate | 2026-09-08 | 2026-09-08 | 100 | 0 | 2026-09-08 | 100% | Complete
T051 | Operator interface: Release gate | 2026-08-26 | 2026-08-26 | 100 | 0 | 2026-08-26 | 100% | Complete
T056 | Integration build: Release gate | 2026-10-28 | 2026-10-28 | 0 | 0 | 2026-11-02 | 25.38% | At risk
T061 | Release qualification: Release gate | 2026-10-20 | 2026-11-23 | 0 | 24 | 2026-11-27 | 0% | At risk
T066 | Supplier qualification: Readiness gate | 2026-05-26 | 2026-05-26 | 100 | 0 | 2026-05-26 | 100% | Complete
T071 | Long lead procurement: Readiness gate | 2026-05-29 | 2026-07-14 | 100 | 32 | 2026-07-14 | 0% | Complete
T076 | Spares provisioning: Readiness gate | 2026-07-10 | 2026-07-10 | 100 | 0 | 2026-07-10 | 100% | Complete
T081 | Maintenance planning: Readiness gate | 2026-07-20 | 2026-09-02 | 100 | 32 | 2026-09-02 | 0% | Complete
T086 | Training development: Readiness gate | 2026-09-03 | 2026-09-03 | 100 | 0 | 2026-09-03 | 100% | Complete
T091 | Support readiness: Readiness gate | 2026-09-03 | 2026-10-19 | 0 | 32 | 2026-10-21 | 0% | Missed
T096 | Bench verification: Evidence gate | 2026-12-22 | 2027-01-15 | 0 | 18 | 2027-01-25 | 0% | At risk
T101 | Environmental qualification: Evidence gate | 2026-12-14 | 2027-01-07 | 0 | 18 | 2027-01-18 | 0% | At risk
T106 | Ground integration: Evidence gate | 2027-02-10 | 2027-03-08 | 0 | 18 | 2027-03-18 | 0% | At risk
T111 | Taxi readiness: Evidence gate | 2027-02-05 | 2027-03-03 | 0 | 18 | 2027-03-16 | 0% | At risk
T116 | Flight research campaign: Evidence gate | 2027-03-29 | 2027-04-22 | 0 | 18 | 2027-05-05 | 0% | At risk
T121 | Test evidence closure: Evidence gate | 2027-03-29 | 2027-04-22 | 0 | 18 | 2027-05-06 | 0% | At risk
T126 | Configuration freeze: Acceptance gate | 2027-05-13 | 2027-06-08 | 0 | 18 | 2027-06-25 | 0% | At risk
T131 | Documentation release: Acceptance gate | 2027-05-18 | 2027-06-11 | 0 | 18 | 2027-06-30 | 0% | At risk
T136 | Acceptance inspection: Acceptance gate | 2027-07-07 | 2027-08-02 | 0 | 18 | 2027-08-20 | 0% | At risk
T141 | Operator training: Acceptance gate | 2027-07-02 | 2027-07-28 | 0 | 18 | 2027-08-17 | 0% | At risk
T146 | Transfer preparation: Acceptance gate | 2027-08-26 | 2027-09-21 | 0 | 18 | 2027-10-13 | 0% | At risk
T151 | Program closeout: Acceptance gate | 2027-08-26 | 2027-09-21 | 0 | 18 | 2027-10-13 | 0% | At risk
T152 | Final demonstrator acceptance | 2027-08-26 | 2027-09-21 | 0 | 18 | 2027-10-14 | 0% | At risk
Formulas:
Slip workdays = IF([Current finish]>=[Baseline finish],NETWORKDAYS([Baseline finish],[Current finish])-1,-(NETWORKDAYS([Current finish],[Baseline finish])-1))

## Risks
Risk register and expected impact
Fictional, unclassified. Status 18 Sep 2026. Derived forecast/SRA fields are Python snapshots.
Risk | Title | Probability | Low days | Mode days | High days | Expected days | Affected task | Owner | Mitigation | Status
RISK-01 | Avionics interface rework | 35% | 8 | 16 | 30 | 6.3 | T047 | Software lead | Freeze interfaces and hold weekly integration reviews | Open
RISK-02 | Environmental retest | 30% | 10 | 20 | 35 | 6.5 | T097 | Test lead | Run prequalification screening before chamber booking | Open
RISK-03 | Instrument delivery delay | 25% | 8 | 15 | 25 | 4 | T092 | Supply lead | Qualify an alternate supplier | Open
RISK-04 | Ground test discrepancy | 40% | 5 | 12 | 22 | 5.2 | T102 | Test lead | Add an early dry run | Open
RISK-05 | Review team congestion | 40% | 3 | 8 | 15 | 3.4667 | T027 | Quality lead | Reserve named reviewers | Open
RISK-06 | Training material revision | 20% | 4 | 8 | 16 | 1.8667 | T137 | Logistics lead | Pilot the training package | Open
RISK-07 | Acceptance documentation gap | 30% | 3 | 7 | 12 | 2.2 | T132 | Delivery lead | Perform an evidence completeness review | Open
RISK-08 | Integration build regression | 35% | 5 | 12 | 24 | 4.7833 | T052 | Software lead | Automate regression tests | Open
RISK-09 | Flight research weather window | 30% | 5 | 10 | 20 | 3.5 | T112 | Test lead | Reserve contingency windows | Open
RISK-10 | Configuration discrepancy | 25% | 3 | 6 | 12 | 1.75 | T122 | Configuration lead | Audit as-built records early | Open

## Changes
Schedule change requests
Fictional, unclassified. Status 18 Sep 2026. Derived forecast/SRA fields are Python snapshots.
Request | Task | Field | Before | Requested | Status | Requested on | Decision date | Owner | Reason | Applied
CR-001 | T058 | duration | 16 | 40 | Approved | 2026-08-24 | 2026-08-28 | Program manager | Expanded telemetry interface verification | TRUE
CR-002 | T097 | duration | 8 | 13 | Pending | 2026-09-14 |  | Test lead | Additional environmental screening | FALSE
CR-003 | T152 | deadline | 2027-08-26 | 2027-09-23 | Rejected | 2026-09-10 | 2026-09-17 | Program manager | Request to move acceptance commitment | FALSE

## History
Approval event history
Fictional, unclassified. Status 18 Sep 2026. Derived forecast/SRA fields are Python snapshots.
Request | Timestamp | Actor | From | To | Decision record
CR-001 | 2026-08-24T09:00:00 | Program manager | Draft | Submitted | Expanded telemetry interface verification
CR-001 | 2026-08-28T15:00:00 | Fictional change control board | Submitted | Approved | Forecast update only. Original baseline remains frozen.
CR-002 | 2026-09-14T09:00:00 | Test lead | Draft | Submitted | Additional environmental screening
CR-003 | 2026-09-10T09:00:00 | Program manager | Draft | Submitted | Request to move acceptance commitment
CR-003 | 2026-09-17T15:00:00 | Fictional change control board | Submitted | Rejected | Forecast update only. Original baseline remains frozen.

## Health
Schedule-health assessment
Fictional, unclassified. Status 18 Sep 2026. Derived forecast/SRA fields are Python snapshots.
Point | Indicator | Numerator | Denominator | Result | Threshold | Direction | Status | Population and method
1 | Missing logic | 0 | 58 | 0 | 0.05 | max | PASS | Incomplete non-milestone activities
2 | Leads | 0 | 117 | 0 | 0 | max | PASS | Relationships into incomplete tasks
3 | Lags | 15 | 117 | 0.12821 | 0.05 | max | REVIEW | Relationships into incomplete tasks
4 | Finish-to-start relationships | 87 | 117 | 0.74359 | 0.9 | min | REVIEW | Relationships into incomplete tasks
5 | Hard constraints | 0 | 58 | 0 | 0.05 | max | PASS | Incomplete non-milestone activities
6 | High float | 3 | 58 | 0.051724 | 0.05 | max | REVIEW | Incomplete non-milestone activities
7 | Negative float | 51 | 58 | 0.87931 | 0 | max | REVIEW | Incomplete non-milestone activities
8 | High duration | 0 | 58 | 0 | 0.05 | max | PASS | Incomplete non-milestone activities
9 | Invalid dates | 0 | 58 | 0 | 0 | max | PASS | Incomplete non-milestone activities
10 | Missing resources | 0 | 58 | 0 | 0 | max | PASS | Incomplete non-milestone activities
11 | Missed baseline tasks | 11 | 65 | 0.16923 | 0.05 | max | REVIEW | Detail activities due by status, includes late completions
12 | Critical path test | 600 | 600 | 1 | 1 | min | PASS | Perturbed T058 by 600 workdays; exact 600-day response required
13 | Critical path length index | 244 | 262 | 0.9313 | 0.95 | min | REVIEW | (Remaining calendar span + final deadline float) / remaining span; simplified CPLI
14 | Baseline execution index | 62 | 65 | 0.95385 | 0.95 | min | PASS | All completed detail activities / detail activities baseline-due by status